## At Home Example
AT HOME MODEL PROJECT PLAN
| Name | Predecessors | Resources | Buxton Role Needed | Work | Duration | Start Date | Due Date
| Growth Platform |  |  |  | 133 h | 36 d | 2015-05-11 | 2015-06-30
| (Milestone) - Milestone #1 - Delivered to Client |  |  |  | 15 h | 6 d | 2015-05-11 | 2015-05-18
These are tasks: | Pre-Model Client Research & Hypothesis Development | [5 empty] | 2015-05-11 | 2015-05-11
| Build Competitor Table | Pre-Model Client Research & Hypothesis Development | Jonathan Jacobs | Predictive Analytics |  |  | 2015-05-11 | 2015-05-11
| AGG request/load | Build Competitor Table | Brian Demers | Spatial Analytics |  |  | 2015-05-11 | 2015-05-11
| Finalize sample set & complete stabilization | Build Competitor Table, Receive Client confirmation of DV | Jonathan Jacobs | Predictive Analytics | 2 h | 1 d | 2015-05-11 | 2015-05-11
| Store Class | Finalize sample set & complete stabilization | Jonathan Jacobs | Predictive Analytics | 3 h | 1 d | 2015-05-12 | 2015-05-12
| Meeting to walk through store class with A/M | Store Class | Jonathan Jacobs | Predictive Analytics |  |  | 2015-05-12 | 2015-05-12
| Determine Profiles and Trade Areas (if needed based on store class results) | Meeting to walk through store class with A/M | Jonathan Jacobs | Predictive Analytics | 1 h | 0.5 d | 2015-05-13 | 2015-05-13
| Load Profiles to SCOUT | Determine Profiles and Trade Areas (if needed based on store class results) | Jonathan Jacobs | Predictive Analytics | 1 h | 0.5 d | 2015-05-13 | 2015-05-13
| Verify SCOUT Load | Load Profiles to SCOUT | Clarizen Admin | Project Management |  |  | 2015-05-13 | 2015-05-13
| Milestone #1 - Deliverable Creation/Review with Team Lead & Hand off to A/M - Stabilization, Store Class, Sample Set, Trade Area, Profiles, Macro WIMC | Load Profiles to SCOUT | Jonathan Jacobs | Predictive Analytics | 6 h | 1 d | 2015-05-14 | 2015-05-14
| AMQC - QC of Milestone #1 | Milestone #1 - Deliverable Creation/Review with Team Lead & Hand off to A/M - Stabilization, Store Class, Sample Set, Trade Area, Profiles, Macro WIMC | Clarizen Admin | Project Management | 1 h | 1 d | 2015-05-15 | 2015-05-15
| Deliver Milestone #1 to Client | AMQC - QC of Milestone #1 | Clarizen Admin | Project Management | 1 h | 1 d | 2015-05-18 | 2015-05-18
| (Milestone) - Milestone #2 - Delivered to Client | Milestone #1 - Deliverable Creation/Review with Team Lead & Hand off to A/M - Stabilization, Store Class, Sample Set, Trade Area, Profiles, Macro WIMC |  |  | 70.5 h | 18 d | 2015-05-15 | 2015-06-10
| Gravity |  | Jonathan Jacobs | Predictive Analytics | 6 h | 2 d | 2015-05-15 | 2015-05-18
| Generate all variables for modeling | AGG request/load, Gravity | Jonathan Jacobs | Predictive Analytics | 10 h | 2 d | 2015-05-19 | 2015-05-20
| Build Models | Generate all variables for modeling | Jonathan Jacobs | Predictive Analytics | 30 h | 6 d | 2015-05-21 | 2015-05-29
| pre-meeting 1 with RS team | Build Models | Jonathan Jacobs | Predictive Analytics | 3.5 h | 1 d | 2015-06-01 | 2015-06-01
| Adjust Models after pre-meeting 1 | pre-meeting 1 with RS team | Jonathan Jacobs | Predictive Analytics | 4 h | 2 d | 2015-06-02 | 2015-06-03
| Meeting #1 | Adjust Models after pre-meeting 1 | Jonathan Jacobs | Predictive Analytics | 2 h | 1 d | 2015-06-04 | 2015-06-04
| Adjustments to model after meeting 1 | Meeting #1 | Jonathan Jacobs | Predictive Analytics | 3 h | 1 d | 2015-06-05 | 2015-06-05
| Milestone #2 - Deliverable Creation/Review with Team Lead & Hand off to A/M - Gravity, recommended model variables | Adjustments to model after meeting 1 | Jonathan Jacobs | Predictive Analytics | 5 h | 1 d | 2015-06-08 | 2015-06-08
| AMQC - QC of Milestone #2 | Milestone #2 - Deliverable Creation/Review with Team Lead & Hand off to A/M - Gravity, recommended model variables | Clarizen Admin | Project Management | 2 h | 1 d | 2015-06-09 | 2015-06-09
| Cann / Identify Cann Groupings | Milestone #2 - Deliverable Creation/Review with Team Lead & Hand off to A/M - Gravity, recommended model variables | Jonathan Jacobs | Predictive Analytics | 4 h | 2 d | 2015-06-09 | 2015-06-10
| Deliver Milestone #2 to Client | AMQC - QC of Milestone #2 | Clarizen Admin | Project Management | 1 h | 1 d | 2015-06-10 | 2015-06-10
| (Milestone) - Milestone #3 - Delivered to Client | Milestone #2 - Deliverable Creation/Review with Team Lead & Hand off to A/M - Gravity, recommended model variables |  |  | 47.5 h | 16 d | 2015-06-09 | 2015-06-30
| Prepare Model Automation Spreadsheet |  | Jonathan Jacobs | Predictive Analytics | 4 h | 2 d | 2015-06-09 | 2015-06-10
| Model Automation & Forecast Verification | Prepare Model Automation Spreadsheet | Jonathan Jacobs | Predictive Analytics | 15 h | 3 d | 2015-06-11 | 2015-06-15
| GIS Hand-off | Model Automation & Forecast Verification | Jonathan Jacobs | Predictive Analytics | 1.5 h | 1 d | 2015-06-16 | 2015-06-16
| Run & Review NQC | GIS Hand-off | Jonathan Jacobs | Predictive Analytics | 4 h | 1 d | 2015-06-17 | 2015-06-17
| Run QC Market Study/Produce QC Site Score | Run & Review NQC | Brian Demers | Spatial Analytics | 8 h | 3 d | 2015-06-18 | 2015-06-22
| Model Error Corrections (Research) - as needed | Run QC Market Study/Produce QC Site Score | Jonathan Jacobs | Predictive Analytics | 8 h | 3 d | 2015-06-23 | 2015-06-25
| QC Market Study Review Meeting | Model Error Corrections (Research) - as needed | Brian Demers | Spatial Analytics | 1 h | 1 d | 2015-06-26 | 2015-06-26
| Final Deliverable Creation/Review with Team Lead & Hand off to A/M | Model Error Corrections (Research) - as needed | Jonathan Jacobs | Predictive Analytics | 3 h | 1 d | 2015-06-26 | 2015-06-26
| AM QC Presentation and Compile Questions | Final Deliverable Creation/Review with Team Lead & Hand off to A/M | Clarizen Admin | Project Management | 1 h | 1 d | 2015-06-29 | 2015-06-29
| Meeting 2 with Project Team | AM QC Presentation and Compile Questions | Clarizen Admin | Project Management | 2 h | 1 d | 2015-06-30 | 2015-06-30
| Working Day - Make any necessary changes | Meeting 2 with Project Team | Jonathan Jacobs | Predictive Analytics |  |  | 2015-06-30 | 2015-06-30
| AM Team Review | Working Day - Make any necessary changes | Clarizen Admin | Project Management |  |  | 2015-06-30 | 2015-06-30
| Formal Run Through with Outside Group | AM Team Review | Clarizen Admin | Project Management |  |  | 2015-06-30 | 2015-06-30
| Deliver Final Presentation - Milestone #3 | Formal Run Through with Outside Group | Clarizen Admin | Project Management |  |  | 2015-06-30 | 2015-06-30

## Example Template
Growth Platform
| Name | Predecessors | Resources | Buxton Role Needed | Work | Duration | Start Date | Due Date
Milestone #1 - Ready Test Environment
Task 1: | Ready iPads for testing | iPad imaging | Gregg | Scout Dev | 4h | 1 | 2015-05-28 | 2015-05-28
Task 2: | Ready Desktop PCs for testing | Desktop imaging | Charles/Gregg | IT / Scout Dev | 16h | 2 | ??
Task 3: | Ready Macbook for testing | Apple Store | Charles | IT | 8h | 1 | 2015-06-10 | 2015-06-11
Task 4: | Create "how to test" document |  | Gregg | Scout Dev | 8h | 1 | ??
Task 5:
Milestone #2 - Begin Testing
Task 1: | Test SCOUT on iPads / tablets | Ready iPads for testing | Gregg | Scout Dev |  | ?? | ??
Task 2: | Test SCOUT on different PCs and monitor sizes | Ready Desktop PCs for testing | Gregg | Scout Dev |  | ?? | ??
Task 3: | Test different versions of IE | Ready Desktop PCs for testing | Gregg | Scout Dev |  | ?? | ??
Task 4: | Report/ prioritize actual bugs | Testing…… | Gregg | Scout Dev |  | ?? | ??
Task 5:
Milestong #3 - Bug fixes
Task 1: | Fix highest priority |  | Scout Dev | Scout Dev |  | ?? | ??
Task 2: | Test fixes |  | Gregg | Scout Dev |  | ?? | ??
Task 3: | Fix middle priority |  | Scout Dev | Scout Dev |  | ?? | ??
Task 4: | Test fixes |  | Gregg | Scout Dev |  | ?? | ??
Task 5: